## Summary-GroupIterationProgress
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks
0 | 1/27 - 2/17
1
2
3

## projectcontribution
You should clearly describe your contribution to the group project in each category. (This is not the final iteration contribution. It is the whole semester contribution)
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Dinara | 6. Configuration Management Plan
Jay | Overview, Related Work, Requirement Anaylsis |  |  |  | Requirement Leader Presentation

## Pelin
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/06-09/13 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
1 | 1/27 - 2/3 | 5 | 4 | 1 | 0-Learn GitHub and Python Flask. Read several tutorials. 5-Discuss project idea with the team and requirements. 6-Setup GitHub | 1 |  |  |  |  | 1 | 1 |  | 1. Set up git and practise basic commads
2 | 2/3 - 2/10 | 6 | 5 | 1 | 0-Research QA. 5-Discuss the frontend and backend with team members 7-Research ways to store data on GitHub | 2 |  |  |  |  | 1 |  | 2
3 | 2/10 - 2/17 | 7 | 5 | 2 | 0-Learn QA. JS and Python. 1- Define high level requirements. 5- Discuss design with team members, make project plans and discuss iteration 0 presentation. 6- Complete the frontend assignment. 7-Prepare QA presentation for iteration 0. | 3 | 1 |  |  |  | 2 |  | 4

## Chenghao
The example shows below. Only include the time that you use to work on the project.
Lead Roles: security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27 - 2/3 | 5.5 | 4.5 | 1.5 | 0 - learn data security 7 - lab assignment | 4 | [6 empty] | 0.5 | learning |  |  | continue to learn data security; start programming; finish SPPP part 7 and 8
2 | 2/3 - 2/10 | 4 | 5.5 | 1 | 0 - learn data security 3 - SPPP part 7 and 8 7 - start passwordManager | 4 |  |  | 0.5 |  |  |  | 1 | SPPP part 7 and 8; learning; passwordManager file | Decryption and encryption | plan to use salt on encryption | continue to learn data security; prepare for presentation; group assignment (footer); correct issues of passwordManager
3 | 2/10 - 2/17 | 8 | 6 | 2 | 0 - learn data security 7 - fix issues of passwordManager; add new code for test | 4 | [6 empty] | 2 | Updating passwordManager file; learning

## Dinara
Lead Roles: Backup Project Leader, Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27 - 2/3 | 5 | 4 | 1 | 0. Learned Github 2. Researched website design tools, tried them out 5. Meeting | 2 |  | 1 |  |  | 1
2 | 2/3 - 2/10 | 9 | 8 | 1 | 0. Learned Python Flask 1. Worked on SPPP part 6 2. Created website design with "justinmind" 5. MoM, Meeting | 3 | 2 | 2 |  |  | 1
3 | 2/10 - 2/17 | 9 | 7 | 2 | 0. Learned Pivotal Tracker 1. Worked on iteration 0 presentation 2. Created front end folders and started html and css coding 5. MoM, Meeting | 2 | 1 | 2 |  |  | 2

## Eli
The example shows below. Only include the time that you use to work on the project.
Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27 - 2/3 | 5 | 3 | 1 |  | 3 | 1 |  |  |  | 1 | 1 |  | started creating objects for items, orders, accounts | data storage: saved python objects or cloud storage? | python objects for now |  | 5
2 | 2/3 - 2/10 | 5 | 3 | 2 |  | 2 | 2 | 1 | [5 empty] | created flask py file to demo web app to group |  |  |  | 5
3 | 2/10 - 2/17 | 6 | 2 | 2 |  | 2 |  | 2 | 2 |  |  |  |  | worked on product display section of home page |  |  |  | 6

## Jay
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 1/27 - 2/3 | 9.5 | 6.5 | 1.5 | 0 - learn git, read tutorial for git and pivotal tracker 1 - start pivitol tracker for requirement analysis 2 - outline a design and structure of web app 5 - having a design meeting(Dinara) and team meeting 6 - set up our team git 7 - research similar web app | 3 | 1 |  |  |  | 1.5 | 3 | 1
2 | 2/3 - 2/10 | 8 | 7 | 1 | 0 - learn pivitol tracker 1 - manage pivitol tracker for requirement analysis 5 - having a meeting with requirement leader for presentation 7 - research similar products, prepare presentation | 2 | 3 | 1 |  |  | 1 |  | 1
3 | 2/10 - 2/17 | 8.5 |  | 2 | 0 - learn Flask, CSS, HTTP, pivitol tracker 1 - Collecting the basic requirement for the project 2 - design logo 3 - 4 - 5 - having a design meeting(Dinara) and team meeting 6 - 7 - prepare iteration 0 presentation | 4 | 0.5 | 1 |  |  | 2 |  | 2
4